## MATRIX - System Requirements
1.1 Form Field Types Data Entry
ID | Requirement | Priority | Source | Notes
FE-01 | Manual data entry: open fields for user-entered values | M | [S29] §2.0 Form Field Types L129
FE-02 | Auto-calculated fields using formulas based on other inputs | M | [S29] §2.0 Form Field Types L130
FE-03 | Pre-population: data that connects forms from pre-award to post-award | M | [S29] §2.0 Form Field Types L131
FE-04 | Conditional fields and branching questions | M | [S29] §2.0 Form Field Types L137
FE-05 | One-to-many response types (multiple responses per question) | M | [S29] §2.0 Form Field Types L138
FE-06 | File attachment fields stored with submission | M | [S29] §2.0 Form Field Types L136
FE-12 | Reduce compatibility issues and variability from custom State/Tribal plans and third-party-enabled State annual reports | M | [S29] Top Problems to Solve
1.2 Validation
ID | Requirement | Priority | Source | Conflict
FE-20 | Flexible validation rules engine for calculations or comparisons to prior form submissions | M | [S29] §2.0 Validation L133
FE-21 | Hard errors (blocking) and warning/notification validations | M | [S29] §2.0 Validation L134
FE-22 | Field-level, field-group-level, and form-level validation | M | [S29] §2.0 Validation L135
FE-23 | Automated data validation using business logic during form completion | M | [S29] Top Problems to Solve
FE-24 | Automated comparison to integration data (e.g., UEI mismatches via SAM.gov) | ? | [S29] Top Problems to Solve; [S37] | Same list as FE-23; no basis in [S29] to differentiate priority; [S37] specifies SAM.gov as external registry
FE-25 | CONFLICT — Validation timing: During data entry vs. review-page-only | M | [S29] §2.0 Validation — "while a grant-recipient fills out a form" | Resolution needed. [S29] implies inline feedback during entry. Implementation spec [S21] proposes review-page-only validation with partial saves of invalid data.
1.3 Version Control Data Integrity
ID | Requirement | Priority | Source | Notes
FE-30 | Multiple simultaneous form versions maintaining existing submission data | M | [S29] §2.0 Version Control L113
FE-31 | Robust version history: federal staff can view submission state at various workflow points | M | [S29] §2.0 Version Control L115
FE-32 | Historical comparison: recipients view past submissions comparatively | M | [S29] §2.0 Version Control L116
1.4 Form Builder
ID | Requirement | Priority | Source | Notes
FE-40 | Low-code/no-code form builder for non-technical staff | C | [S29] §2.0 Accessibility & Design L162 — "after year 1" | Explicitly out of MVP scope per [S21]
FE-41 | Sandbox/testing space for form builder | C | [S29] §2.0 Accessibility & Design L162 | Post-year-1
FE-42 | Enable new forms to be designed, updated, and tested more quickly by program staff | M | [S29] Top Problems to Solve | Long-term goal; MVP uses hard-coded Python schemas
2 Form Submission Workflow Wf
ID | Requirement | Priority | Source | Conflict
WF-01 | Auto-create and initialize forms for recipients with pre-populated data based on reporting schedules | M | [S29] §2.0 Workflow L120
WF-02 | Show trends over time using previous year data | M | [S29] §2.0 Workflow L120
WF-04 | Recipients can "unsubmit" forms | M | [S29] §2.0 Workflow L122
WF-05 | Recipients can submit revisions to submitted forms | M | [S29] §2.0 Workflow L122; [S24] Req #8 | Absorbs WF-08
WF-09 | Customizable multi-step, multi-person federal review and approval | M | [S29] §2.0 Workflow L123 | Out of MVP scope per [S21]
WF-10 | Visual/no-code workflow builder for review processes | C | [S29] §2.0 Workflow L123 — "ideally managed through a visual/no-code workflow builder" | Post-MVP; "ideally" = aspirational, not a Should
WF-11 | Save progress and return later to make revisions | M | [S29] §2.0 User Experience L172; [S29] Task Area 2 | Absorbs AD-07; [S21] confirms partial saves with invalid data allowed
WF-12 | Previously submitted data available in forms to limit repeat data requests | M | [S29] §2.0 User Experience
WF-13 | Customizable real-time alerts and notifications linked to workflow events | M | [S29] §2.0 Workflow L124 | Out of MVP scope per [S21]
WF-14 | Deadline-aware notifications | M | [S29] §2.0 Collaboration & Workflow Mgmt L124 — "deadlines and notifications"; [S29] §2.0 Workflow — "form past due" in notification examples
WF-15 | Workflow for multiple users entering data into one form, routing, updating/returning for re-submission | M | [S29] §2.0 Workflow L121; §2.0 Collaboration | Absorbs WF-03; Out of MVP scope per [S21]
WF-17 | Tracking and collaboration visibility on forms between program staff, lead agencies, and sub-recipients across submission, review, and revision lifecycle | M | [S29] Top Problems to Solve | CQI (Continuous Quality Improvement) sprints are a specific collaboration workflow consuming this visibility ([S03], [S05])
WF-18 | March 31 statutory submission deadline for CSBG Annual Reports per CSBG Act §678(b) | M | [S15] — "ensures grant recipient compliance as outlined in Section 678(b) of the CSBG Act" | Recurring annual deadline; system should enforce/notify per WF-14
3 Authentication Security As
ID | Requirement | Priority | Source | Conflict
AS-01 | Authentication with Login.gov | M | [S29] §2.0 Security L142
AS-03 | Government users authenticate via login.acf.gov (Okta), NOT Login.gov directly | M | [S10] | Nuance missing from [S29]; gov vs non-gov distinction
AS-04 | Non-government users have separate authentication path (TBD) | ? | [S10] | Risk documented — could delay development or require rework
AS-14 | ATO within 18 months | M | [S29] §2.0 Security L143
AS-16 | SORN (Systems of Records Notice) required | M | [S29] §2.0 Security L144
3.1 Ato Artifacts
ID | Artifact | Status (as of Feb 2026) | Owner | Source
AS-A4 | System Security Plan (SSP) | In Progress (2026-02-23) | — | [S08]
AS-A11 | Security Assessment Plan | In Progress | — | [S08]
AS-A12 | Appendix X (controls implementation) | In Progress | — | [S08] — "as much effort as all other ATO docs combined"
AS-A13 | Interconnection Security Agreement (ISA) | In Progress (ACF template sent) | — | [S08]
AS-A14 | Plan of Action and Milestones (POAM) | In Progress (ACF template sent) | — | [S08]
4 Integration Data Da
ID | Requirement | Priority | Source | Conflict
DA-01 | Flexible read API for forms, submissions, and bulk data extraction | M | [S29] §2.0 Integration L148 | Out of MVP scope per [S21]
DA-02 | Write API to import pre-populated data | M | [S29] §2.0 Integration L149 | Out of MVP scope per [S21]
DA-03 | Data exports via API, CSV, and human-readable formats | M | [S29] §2.0 Integration L150
DA-04 | Export individual form submissions as PDFs | M | [S29] §2.0 Integration L151
DA-05 | Generate public-access links to specific portions of a submission | ? | [S29] §2.0 Integration L152 | No [S29] language differentiates priority from adjacent items; was S without basis
DA-06 | Comprehensive, easy-to-understand API documentation | M | [S29] §2.0 Integration L153
DA-07 | Real-time data access that doesn't hinder application performance | M | [S29] Top Problems to Solve
DA-09 | Data exports feed Performance Management website (Monique Alcantara is COR) | ? | [S05]; [S03] | Downstream consumer not in [S29]; congressional reporting is primary downstream workflow — Melanie manages all congressional reporting ([S03]); data flows: exports → PM website → Congress ([S01], [S29])
DA-10 | OLDC DataConnect or Excel exports as data migration source | ? | [S13] — "Ideal: OLDC DataConnect from GS; Alternative: Excel exports"
DA-12 | Existing XML/XSD validation artifacts from SmartForms available as reference | ? | [S13] | "Migration input" was an inference; source only lists the artifact attachment
DA-13 | FY24 raw data exports exist (State Plan, Modules 1/2/4) for schema reference | ? | [S14] — RVW/RPT prefix naming convention
DA-14 | Enable program staff to easily export, review, and correct data errors (missing data, data conflicts, new elements) | M | [S29] Top Problems to Solve
DA-15 | Conditional-logic-aware PDF/print export: omit non-applicable sections from output | ? | [S03] — "business logic built in, but when they print it, it shows everything (even questions that weren't applicable) - hard to read"
5 Accessibility Design Ad
ID | Requirement | Priority | Source | Notes
AD-01 | Section 508 WCAG AA-compliant front end | M | [S29] §2.0 Accessibility & Design L162
AD-02 | USWDS (United States Web Design System) as design system | M | [S29] §2.0 Accessibility & Design L162 — "ideally using" USWDS | [S29] uses "ideally" for USWDS specifically; 508 AA is the hard requirement
AD-05 | Clear information about user's location in multi-step process | M | [S29] Task Area 2 — "Give users clear information about where they are"
AD-06 | Plain, familiar language throughout the service | M | [S29] Task Area 2
AD-08 | Consistent visual identity with agency branding | S | [S29] Task Area 2
AD-09 | Low-bandwidth/rural environment support | ? | [S06] — Alaska named explicitly | Priority was M per [S24]; needs re-evaluation with allowed sources only. Note: [S06] also documents zero-connectivity on-site assessment scenarios (ANA), which exceeds "low-bandwidth" — gap between AD-09 and full offline capability
AD-13 | In-context field guidance and companion document integration (extends UP-02) | ? | [S06] — "Form itself does not include the substantial context that comes with very lengthy instruction and guide documents"; [S32] | Broader than SF-424M cross-ref (UP-02): field-level help, section instructions, 62–150 page companion docs
6 Permissions User Management Pm
ID | Requirement | Priority | Source | Conflict
PM-01 | Flexible permissions: read, write, and export controls | M | [S29] §2.0 Permissions L177
PM-02 | Self-service user management: recipients manage their own users and permissions | M | [S29] §2.0 Permissions L178
PM-03 | Hierarchical administration: sub-recipient, state, and federal levels | M | [S29] §2.0 Permissions L178
PM-04 | Minimum permission levels: read-only, write-only, approve at each level | M | [S29] §2.0 Permissions L179
PM-05 | Varying permission levels: view-only, view+edit, view+submit | M | [S29] Objective — "varying permission levels"
PM-06 | 75 federal staff with review, route, approve, analyze, compare, export capabilities | M | [S29] Objective — scale assumption
PM-07 | Roles and permissions managed through Okta groups syncing with application | ? | [S10] | Implementation approach
PM-08 | Authorization and access control | M | [S29] §2.0 Permissions | Out of MVP scope per [S21] — CONFLICT
7 Performance Reliability Pr
ID | Requirement | Priority | Source | Notes
PR-02 | Scalable to 1,100 grant recipients + sub-recipients + 75 federal staff | M | [S29] Objective
PR-04 | Real-time system resource utilization monitoring | M | [S29] Task Area 2 — "Use data to drive decisions"
PR-05 | Real-time performance monitoring: response time, latency, throughput, error rates | M | [S29] Task Area 2
PR-06 | Median, 95th percentile, and 98th percentile performance measurement | M | [S29] Task Area 2
PR-07 | Track concurrent users in real-time | M | [S29] Task Area 2
PR-08 | Monitor user behaviors in aggregate | S | [S29] Task Area 2
PR-09 | Multivariate/A/B testing support in production | C | [S29] Task Area 2 — "as needed"
PR-10 | 24/7 operational availability | M | [S29] Task Area 3 L349 — "operational 7 days per week, 24 hours per day"
8 Success Criteria Sc
ID | Criterion | Source | Conflict
SC-01 | 20+ Tribal grant recipients submit via CORE without reverting to PDFs | [S24] Obj 1 KR; [S21] Goal 1 | Conflicts with other sources suggesting 10-12 pilot cohort
SC-02 | ≥80% of users report digital experience is easier than PDFs | [S24] Obj 3 KR; [S21] Goal 3 (item 3.i)
SC-03 | 100% Section 508 compliance | [S24] Obj 3 KR; [S39] | VPAT verification required per AD-11; also AC criterion
SC-04 | Zero ACF OCIO security or compliance findings | [S24] Obj 3 KR
SC-05 | Architecture documentation complete for Phase II | [S24] Obj 2 KR
SC-06 | Platform supports both simple and complex forms | [S24] Obj 2
SC-07 | Establish first measurable baseline for Tribal reporting performance | [S24] — "CORE provides the first measurable baseline"
9 Form Inventory Fi
ID | Form Name | Phase | Users | Source
FI-01 | CSBG Tribal Plan and Application | Phase I | ~66 | [S29] Phase I; [S13]
FI-02 | CSBG Tribal Annual Report | Phase I | ~30 (up to 66) | [S29] Phase I; [S13] | [S29] uses "CSBG Tribal Annual Report (OMB Approved Form)"; "(Long Form)" is informal shorthand. Tribal reports have 3 modules (not 4): M1=Tribal Admin, M2=Tribal Expenditures, M3=Individual/Family.
FI-03 | CSBG Tribal Annual Report [Short Form] | Phase I | ~30 (up to 66) | [S29] Phase I; [S13] — $50k funding threshold determines which form | [S29] uses bracket notation [Short Form]
FI-04 | CSBG Eligible Entity List | Phase II | — | [S29] Phase II — OMB Approved Doc (not Form)
FI-05 | CSBG State and Territory Plan | Phase II | 53+ | [S29] Phase II
FI-06 | CSBG Annual Report 3.0 (Modules 1-4) | Phase II | 53+ | [S29] Phase II; [S15] — Modules: M1=State Administration, M2=Agency Expenditures/Capacity/Resources, M3=Community Level, M4=Individual and Family Level | M3 and M4 were previously swapped; corrected per [S15] (IM #152). M1 completed by state lead agencies; M2-M4 by eligible entities.

## MATRIX - Implementation Decisio
Form Engine
ID | Decision | Source | Notes
FE-08 | Interview-style page-by-page data entry flow via POST | [S21] | Implements FE-01 through FE-07
FE-09 | JSON field storage for form entry data in FormEntry model | [S21]
FE-10 | Python/Pydantic schemas as single source of truth for UI structure, validation rules, and UX definition | [S21] | Schema has 3 parts: metadata, Django Form class, UX definition
FE-11 | FormDefinition records contain schema class name linking to Python schema | [S21]
FE-33 | Form status lifecycle: draft → submitted → amended → archived | [S21] | "amended" = revision after submission; "archived" = available but hidden from user view
FE-35 | Detailed field-level change logging via FormAuditDetail model | [S21] | Extends FE-34 (audit trail requirement)
FE-36 | Short form variant derived from long form base with simplified field set | [S31] | Clarifies FI-02/FI-03 relationship; UI must differentiate variants
FE-37 | Cross-form pre-population: Tribal Plan pre-populates from Tribal AR data | [S31] | Extends FE-03; requires shared field identifiers across form schemas
FE-38 | Periodic auto-save every 30-60 seconds with success/failure messaging | [S31] | Implements WF-11; implies debounced persistence and conflict handling
FE-39 | PDF generation uses review page data, not raw form data | [S31] | Clarifies DA-08; review page aggregation is a dependency for PDF export
FE-43 | Screener flow: routing UI after login that determines which form a user fills out | [S36] | Form-selection component; not in prior context
FE-44 | Client-side caching via IndexedDB/localStorage for connection resilience; sync on reconnect | [S36] | Prescribed browser storage APIs; requires service worker or connection-monitoring layer
FE-45 | Three connection state indicators: "Saved", "Connection lost — work stored locally", "Reconnected — sync successful" | [S36] | Implements AD-09/PR-14 low-connectivity UX
FE-46 | UEI (Unique Entity Identifier) as cross-form pre-population key | [S36] | Extends FE-03/FE-37; Authorized Official inputs UEI-keyed data
FE-47 | Concurrent edit conflict handling for periodic auto-save (extends FE-38) | [S21] — "Simultaneous multi-user editing" listed as known concern
Authentication
ID | Decision | Source | Notes
AS-05 | Authorization Code Flow with PKCE + client secret; all token handling server-side (browser receives only Django session cookie) | [S27] | Implements AS-01/AS-02 auth requirements
AS-06 | Keycloak (oauth.csfeer:8081) for local development mock | [S27] | Realm: csfeer, client: csfeer-auth
AS-07 | Role-to-group mapping from JWT realm_access.roles claims | [S27] | Critical open question — will Okta/Login.gov token emit roles in realm_access.roles structure (Keycloak convention), or will backend need updating for different claim structure?
AS-08 | Role mappings: csfeer_admin → staff+superuser; csfeer_staff → staff; superuser → superuser; any other role → Django group created/assigned by name | [S27] | Fourth mapping carries security implications — unexpected roles auto-create groups
AS-09 | Token lifetimes: access 5min, session idle 30min, session max 10hr | [S27] | Keycloak dev config values — production Okta settings not yet confirmed
AS-10 | Auto-provision user (by email claim), OrganizationProfile, and UserOrganizationMembership (role: admin) on first login; store sub claim in UserProfile.oidc_user_id | [S27]
AS-11 | Group memberships cleared and re-synced from token on every login | [S27]
AS-12 | RP-initiated logout with Okta session termination | [S27]
AS-18 | MVP uses basic session management without Login.gov; Login.gov integration deferred | [S31] | Story 1.3; clarifies AS-01 is not in MVP scope
Data
ID | Decision | Source | Notes
DA-08 | PDF generation via WeasyPrint (HTML/CSS to PDF) | [S18] | Implements DA-04; conflicts with any "headless Chrome" references

## MATRIX - Internal Requirements
Form Engine
ID | Requirement | Priority | Source | Notes
FE-07 | Support both simple and complex forms (complexity spectrum) | M | [S24] Obj 2
FE-34 | Audit trail for all form actions by user | M | [S24] Req #19; [S21] — FormAuditTrail model
[WS-01] | Data sensitivity classification per field | ? | Derived: AS-20 (CUI) + PM-01 (access controls) imply per-field tiers | Stretch
[WS-02] | PRA metadata per form (OMB number, expiration, burden) | ? | Derived: FI-01–FI-06 + [S03], [S05], [S13] PRA notes | Operational dependency; stretch
[WS-03] | Schema-driven definitions decoupled from hardcoded UI | ? | Derived: FE-10 + FE-42 + FE-40 | Direction for post-MVP form builder
Workflow
ID | Requirement | Priority | Source | Notes
WF-06 | Submit a form (distinct action) | M | [S24] Req #5
WF-07 | Submit a report (distinct from form?) | ? | [S24] Req #7 | May be duplicate of WF-06; early conceptual distinction
WF-16 | Four-stage deliverable approval: draft → gov't comments → final → GTM/COR acceptance | ? | [S16]; [S17] | Misplaced — contract deliverable workflow, not form submission; belongs in § 12 governance
[WS-07] | Conditional routing based on submission attributes (e.g., budget threshold triggers CFO step) | ? | Derived: [S37] open question | Post-MVP; depends on WF-09
[WS-08] | Parallel approval branches with join logic | ? | Derived: [S37] open question | Post-MVP; depends on WF-09
[WS-09] | Delegation and escalation rules for review workflows | ? | Derived: [S37] open question | Post-MVP; depends on WF-09
Authentication Security
ID | Requirement | Priority | Source | Notes
AS-02 | OIDC via Okta (acf.okta.com) as identity broker | M | [S27]
AS-13 | Client secret must be stored in secrets manager (e.g., AWS Secrets Manager); rotation schedule TBD | M | [S27] | Storage is M ("must never be hardcoded"); rotation schedule is S
AS-15 | ATO target date: May 29, 2026 | M | [S12] | Specific milestone from compliance tracker
AS-17 | PIA (Privacy Impact Assessment) required | M | [S12] — status "UNDER REVIEW" as of 2026-02-09 | [S29] §2.0 Security does NOT mention PIA; sourced from ATO process only
AS-19 | Zero Trust strategy required per EO 14028 | M | [S33] | Contractor must provide ZT strategy
AS-20 | CUI handling per NIST standards for Controlled Unclassified Information | M | [S33]
AS-21 | AI policy: federal data cannot train commercial AI models without approval | M | [S33] | Must comply with US law + ACF policy
AS-22 | Personnel security: background investigations, NDAs, annual security/privacy/records training | M | [S33]
AS-23 | High-risk Public Trust clearance required for contractor staff | M | [S34] | PWS page 40/67; affects onboarding timelines for new team members
AS-24 | Incident response SLAs: Critical <1hr, High <4hrs, Medium <24hrs, Low <72hrs | M | [S35]
Ato Artifacts From S12 Compliance Tracker
ID | Artifact | Status (as of Feb 2026) | Owner | Source
AS-A1 | ACF System Registration Form | COMPLETED (2026-01-27) | Diana Rosner (CTR) | [S12]
AS-A2 | Privacy Impact Assessment Form | UNDER REVIEW (2026-02-09) | Ablavi Zolome (CTR) | [S12]
AS-A3 | System-Categorization | UNDER REVIEW (2026-02-20) | Oyindasola Akisanmi (CTR) | [S12]
AS-A5 | Business Impact Analysis (BIA) | Unknown (blank in tracker) | — | [S12]
AS-A6 | Incident Response Plan (IRP) | Unknown (blank in tracker) | — | [S12]
AS-A7 | Contingency Plan | Unknown (blank in tracker) | — | [S12]
AS-A8 | Configuration Management Plan | Unknown (blank in tracker) | — | [S12]
AS-A9 | E-Authentication Agreement | Unknown (blank in tracker) | — | [S12]
AS-A10 | Selected Controls Rev5-Low_System | Unknown (blank in tracker) | — | [S12]
Integration Data
ID | Requirement | Priority | Source | Notes
DA-11 | Pre-population limited to "high-confidence data only" for MVP | ? | [S16]; [S17] — risk mitigation strategy
Accessibility Design
ID | Requirement | Priority | Source | Notes
AD-04 | Optimized for tablets and laptops | M | [S24] NFR6
AD-10 | Prototype designs may vary from implementation based on USWDS component feasibility | ? | [S20] | Implementation variance caveat
AD-11 | Accessibility Conformance Report (ACR) via VPAT required for any commercial ICT | M | [S33] | Gov't reserves right to independently test; remediation at contractor expense
AD-12 | WCAG 2.0 AA is contractual obligation; building to WCAG 2.1/2.2 AA is advisable | ? | [S33] | 2.0 is outdated; 2.1/2.2 is current standard
[WS-11] | Offline-first field administration (ANA, CB on-site assessment) | ? | Derived: AD-09 + FE-44 + [S06] — "ANA — offline/in-person administration needed" | Post-MVP; exceeds low-bandwidth (AD-09) into full offline
Performance Reliability Nfrs
ID | Requirement | Priority | Source | Notes
PR-01 | Form load/save ≤ 3 seconds on typical 4G connection | M | [S24] NFR1
PR-03 | ≥ 99.5% uptime excluding scheduled maintenance | M | [S24] NFR3
PR-11 | ≥ 200 concurrent users | M | [S24] NFR2
PR-12 | FISMA Moderate, FedRAMP hosting, FIPS 140-2 encryption | M | [S24] NFR4 | Relevant to conflict C-3: [S24] explicitly says Moderate
PR-13 | Modern browser support: Chrome, Firefox, Edge, Safari | M | [S24] NFR5
PR-14 | Operate reliably despite poor connectivity (auto-save + local caching) | M | [S24] Req #13 | Connects to AD-09 low-bandwidth constraint
PR-15 | Test coverage: >80% | M | [S35]
PR-16 | 3G network testing required in addition to 4G | M | [S35] | Extends PR-01
PR-17 | Form completion time target: <25 minutes | S | [S35] | UX performance metric
PR-19 | Support volume: <60 tickets/month | S | [S35]
PR-20 | Processing cost: <$50/form | S | [S35]
PR-21 | 75% tribal digital adoption within Year 1 | S | [S35] | Also appears as success metric
Internally Sourced Success Metrics
ID | Metric | Target | Source | Notes
SC-08 | Pilot orgs with successful submission | 100% | [S36]
SC-09 | Submissions passing validation without OCS help | ≥90% | [S35]; [S36] | Absorbs PR-18
SC-10 | Errors resolved without OCS intervention | ≥85% | [S36]
SC-11 | Reduction in OCS follow-up emails | ≥30% | [S36]
SC-12 | Autosave success rate | ≥98% | [S36]
SC-13 | Data loss | 0% | [S36]
SC-14 | User satisfaction | ≥4/5 | [S36] | Relevant to C-9 — different metric than SC-02's "≥80% easier than PDFs"
SC-15 | Help desk tickets per org | ≤1 | [S36]
SC-16 | Submission time reduction | 12-20 days → 3-7 days | [S36] | Aspirational: <1 hour; 1,800 hrs/yr current tribal burden
SC-17 | Component reuse across forms | ≥70% | [S36] | Architecture metric
SC-18 | New form onboarding time | ≤6 weeks | [S36] | Phase II readiness metric
SC-19 | OCS review time reduction | ≥25% (long-term ≥50%) | [S36]
SC-20 | API uptime | ≥99.9% | [S36] | Stricter than system uptime (PR-03: 99.5%)
SC-21 | Form completion time reduction vs legacy PDF | ≥25% | [S39] | Different framing than SC-16 (days-based)
Internally Sourced Success Metrics
Category | Key Metrics
User interaction | Sessions per submission, autosave success ≥98% (SC-12)
Submission quality | Validation passes without help ≥90% (SC-09), errors self-resolved ≥85% (SC-10)
Performance | Load/save ≤3s on 4G (PR-01), p95/p98 latency (PR-06), ≥200 concurrent users (PR-11)
Operational | Tickets <60/mo (PR-19), OCS review time ≥25% reduction (SC-19)
Mvp Acceptance Criteria From S39
ID | Criterion | Source | Notes
AC-01 | All three tribal forms available digitally with validation + save/submit | [S39]
AC-02 | Login.gov working for all pilot users | [S39] | Note: contradicts AS-18 (Login.gov deferred per [S31]); may reflect earlier planning
AC-03 | CSV + PDF export functional | [S39]
AC-04 | At least 10 tribal orgs successfully submit during pilot | [S39] | Lower bar than SC-01 (20+ per [S24]); connects to C-2 (pilot size)

## MATRIX - MVP & Delivery
10 Infrastructure Technology It
ID | Decision | Source | Notes
IT-01 | Python 3.12, Django 6.0+ | [S18]; [S07] — "Tech stack approved"
IT-02 | PostgreSQL (NGSC AWS) | [S18]; [S09] — "proceeding with ECS and Postgres"
IT-03 | AWS ECS (not Kubernetes) | [S09] — resolves PMP vs Helm chart discrepancy
IT-04 | Alpine.js 3.15+ for frontend reactivity | [S18]
IT-05 | USWDS 3.13+ for UI components | [S18]
IT-06 | Django Ninja 1.4+ for REST APIs | [S18] | [S35] PMP says DRF — outdated; Django Ninja is actual framework
IT-07 | WeasyPrint 62.3+ for PDF generation | [S18]
IT-08 | Django Cotton 2.1+ for reusable template components | [S18]
IT-09 | Keycloak for local dev auth mock | [S27] — realm: csfeer, client: csfeer-auth; [S38] | [S38] notes Keycloak is being replaced (low impact); may affect mock-oauth setup
IT-10 | NGSC AWS as production environment | [S07]; [S09]; [S38] | ATO strategy: inherit existing NGSC controls (confirmed at IPT kickoff); environments: Dev/Test, Stage, Prod (lower + upper)
IT-11 | GitLab repository (~Feb 18, 2026) with GitHub mirroring | [S10] | Date inferred from "next Wednesday" relative to Feb 10 meeting
IT-12 | Jira for sprint tracking (project key "FE", RapidView 404) | [S16]; [S17]
IT-13 | Confluence for documentation | [S25]
IT-14 | Figma for design/prototyping — two boards: "ACF-Exploration" (strategy/service blueprint) and "Tribal-Forms" (clickable prototypes V1, V1.3) | [S20]; [S19]
IT-15 | Mural for process maps and research workshops | [S22]; [S03]
IT-16 | Open-source codebase preferred, using standard sustainable open-source libraries | S | [S29] §2.0 Open Source & Scalability — "preferred" | Entire [S29] subsection had no MATRIX entries
IT-17 | Affordable scaling of user licenses (if applicable) | ? | [S29] §2.0 Open Source & Scalability — "if applicable"
IT-18 | PIV cards + GFE required for NGSC access; Zscaler for network access management | M | [S38] | Operationally significant for CI/CD pipeline design
IT-19 | Parallel development: Focus builds in own environment while NGSC provisioning proceeds | — | [S38] | Timeline risk mitigation
IT-20 | ServiceNow ticket process for Okta/Login.gov user provisioning | — | [S38] | Operational integration path
Delivery Sprint Planning
ID | Item | Target | Source | Notes
DL-01 | Landing page deployed | 2026-03-01 | [S31]
DL-02 | Tribal Annual Report (long form) complete | 2026-03-15 | [S31]
DL-03 | Tribal Plan and Application complete | 2026-03-31 | [S31]
DL-04 | ATO documentation package submitted | 2026-03-31 | [S31]
DL-05 | Build sequence: rendering → saving → review page → auto-save → PDF export | — | [S31] | Critical path for March 15 — no flexibility in sequence; each step depends on the previous
DL-06 | 192 story points across 6 epics for Q1 (~11-12 weeks, ~4.75 FTE) | Q1 2026 | [S31] | Aggressive velocity; no benchmarks stated
DL-07 | Shutdown-safe sequencing: ACF-independent work prioritized first | — | [S31] | Government shutdown risk mitigation
DL-09 | API data export endpoints designated as stretch goal | — | [S31] | May be deprioritized if forms slip; relevant to C-4
DL-10 | Rural connection performance optimization as acceptance criterion for data persistence | — | [S31] | Connects to AD-09
DL-11 | Soft launch to 10-12 tribal orgs with white-glove support | Month 9 | [S35] | Weekly check-ins tapering to bi-weekly; connects to C-2 (pilot size)
DL-12 | Wave-based full rollout of remaining orgs | Month 12 | [S35] | After ATO authorization
DL-13 | Stage Gates: Discovery (M2), MVP (M8), Pilot (M9), Continuous Dev (M15) | Various | [S35] | Go/No-Go decision points
DL-14 | ATO timeline: Planning (M1-2), Implementation (M3-8), Assessment (M9-12), Authorization (M12-13); weekly sprint stories | M1-13 | [S31]; [S35] | ATO certification is #1 risk (p×i = 0.45)
DL-15 | 90-day post-launch baseline telemetry: user interaction, submission quality, performance, operational metrics | Post-launch | [S36] | Requires day-one instrumentation; not post-MVP

## MATRIX - Personas & Governance
Persona Derived Requirements
ID | Item | Source | Notes
UP-01 | Three grantee role tiers: Approver (edit + submit/attest), Contributor (edit only), Viewer (read-only + PDF export) | [S32] | More specific than PM-01–PM-05; Viewer role not in prior context
UP-02 | SF-424M cross-referencing: in-context guidance linking CSFEER fields to their SF-424M/OLDC counterparts | [S32] | Recurring tribal pain point; data consistency across systems
UP-03 | Transmittal letter/attestation: distinct artifact requiring signatures, upload tracking, and status visibility | [S32] | Not just a form field; separate workflow artifact
UP-04 | Portfolio dashboard: grantee-level status view (Not Started / In Progress / Submitted / Needs Correction) per form per grantee | [S32] | OCS staff manage 15-25 grantees; current OLDC has no portfolio view
UP-05 | Batch review & structured export: CSV/Excel for cross-grantee comparison and outlier identification | [S32] | Extends DA-03; federal staff compare submissions in batches
UP-06 | Visual diff: per-field "what changed from last year" indicators | [S32] | Extends FE-32; contributors want change indicators on fields
UP-07 | Simplified summary view for leadership (funding amount, major goals, key outcomes) | [S32] | Separate from full dense form; used for council/leadership briefings
UP-08 | Unified admin console: search by org/person/email/UEI, few-click role changes, audit logging | [S32] | Extends PM-02; current process spans OLDC admin, email, spreadsheets
UP-09 | Peak load resilience around reporting deadlines (Tribal Plan dues, March 31 Annual Report) | [S32] | Extends PR-10; system stability during these windows is "non-negotiable"
UP-10 | Feature flags / runtime configuration for policy or OMB form changes without full redeploys | [S32] | Operational resilience; avoids redeploy for policy changes
UP-11 | Degraded network test environments for reproducing real-world low-connectivity issues | [S32] | Testing infrastructure; hard to reproduce issues otherwise
UP-12 | 4-tier support model: in-app help → help desk (email/phone) → tech escalation → on-site | [S35]; [S32] | "In-app help" tier is closest to system feature; connects to AD-13
[WS-12] | Form inventory visibility (what exists, who uses it, submission counts) | Derived: FI-01–FI-06 + FE-42 | Stretch
[WS-13] | PRA tracking per form (Melanie ~half, Monique ~half) | Derived: [S03], [S05], [S13] PRA notes | Operational dependency; stretch
[WS-16] | Congressional reporting tools (Melanie's workflow) | Derived: DA-09 + [S01], [S03], [S29] — exports → PM website → Congress | Post-MVP
[WS-17] | CQI workflow integration (Kayla's sprints) | Derived: WF-17 + [S03], [S05] — CQI consumes collaboration visibility | Post-MVP
[WS-19] | Staff support console with scoped read-only access | Derived: UP-12 + UP-04 | Post-MVP
[WS-20] | Trackable support interactions (category, resolution, time) | Derived: SC-15 (≤1 ticket/org) implies tracking | Post-MVP
Role Permission Matrix From S32
Capability | Approver | Contributor | Viewer | OCS Staff | Admin
Edit form sections | Yes | Yes | No | No | No
Submit / attest | Yes | No | No | No | No
View form data | Yes | Yes | Yes | Yes (read-only) | Yes
Export PDF/CSV | Yes | Yes | Yes | Yes | Yes
Portfolio dashboard | No | No | No | Yes | Yes
Manage users/roles | No | No | No | No | Yes
View audit logs | No | No | No | Limited | Yes
Contract Governance
ID | Item | Source | Notes
CG-01 | Contract: 24-month (12+12); Core: PM, Tech Lead, Product Manager, UX Lead, 2 Sr Full-Stack Devs (6 FTE); Surge: +2 Devs, +0.5 Security, +0.25 A11y (M4-9, M13-15) | [S33]; [S35] | Relevant to C-8; [S33] says ~4.75 FTE, [S35] details 6 FTE + surge
CG-02 | Key personnel: Product Manager requires government approval for replacement | [S33]
CG-03 | Bi-weekly release cadence | [S33] | Aligns with agile methodology
CG-04 | Governance: Project Intake Form within 5 days of award; CFT meetings; Stage Gate Reviews | [S33] | ACF OCIO governance framework
CG-05 | Reporting: bi-weekly dashboard, monthly CSR, semi-annual Mid-Year Performance Summary | [S33]
CG-06 | Transition plan: 4 weeks per [S33], 90 days per [S35] — see C-12 | [S33]; [S35] | Conflict: 4 weeks (2 sprints) vs 90 days (doc audit → training → parallel ops)
CG-07 | Incident response: comply with ACF IRT policy; report all suspected/confirmed incidents | [S33]
CG-09 | Tribal Advisory Group: 6-8 geographically diverse representatives (formed M1-6); 8-10 site visits during discovery | [S35]
CG-11 | Repo and all infrastructure assets transfer to HHS/ACF post-development | [S35]
CG-12 | Open-source contributions planned: USWDS Crispy Forms for Django, USWDS Cotton component framework | [S35] | Aspirational; Crispy Forms not observed in codebase
CG-13 | All IP (research, designs, code, documentation) is property of ACF | [S37] | From PWS
CG-14 | Requirements are non-exhaustive and mutable; agile discovery drives changes; Government is Product Owner | [S37] | From PWS
Phased Rollout
ID | Phase | Scope | Source | Notes
PH-01 | Phase I (MVP) | CSBG Tribal forms (~66 orgs, 3 forms) | [S33]; [S29] | Current scope
PH-02 | Phase II | States/territories opt in; legacy OLDC runs in parallel | [S33] | Dual-track operation required — some users on CORE, some on legacy
PH-03 | Phase III | Full migration of all users; legacy system sunset | [S33] | Requires data migration and feature parity with PDF workflows
PH-04 | Long-term vision | 25,000+ recipients, 100+ forms across all ACF program offices | [S33] | CSBG is first program; multi-program platform

## Requirements Traceability
Field Types Data Entry
ID | Requirement | Status | Jira | Evidence
FE-01 | Manual data entry: open fields | ✅ | bd-427 (epic), bd-18, bd-210, bd-233 | ACFFieldsMeta generates all standard Django field types with ACF prefix
FE-02 | Auto-calculated fields | ✅ | bd-55, bd-89 | CalculatedCurrency/Integer/DecimalField; server-side sum + client-side updateCalculatedFields()
FE-03 | Pre-population: cross-form data linking | ❌ | — | form_start creates blank entries; no cross-form population mechanism
FE-04 | Conditional fields and branching | ✅ | bd-86, bd-114 | ACFFieldFilterField drives fields_to_exclude; remove_nodes_with_excluded_fields() prunes layout tree
FE-05 | One-to-many response types | ❌ | — | No FormSet, repeatable group, or dynamic field mechanism
FE-06 | File attachment fields | ⚠️ | bd-399 | ACFFileField exists; USWDS file_input available; not used in any deployed form, no storage backend
FE-12 | Reduce variability from custom plans | ⚠️ | bd-332 | Standardized schemas enforce structure for tribal forms; state/territory forms not yet built
Validation
ID | Requirement | Status | Jira | Evidence
FE-20 | Flexible validation rules engine | ✅ | bd-114, bd-240, bd-458 | Pydantic+Django form validation with custom field validators and fields_to_exclude logic
FE-21 | Hard errors and warning validations | ⚠️ | — | Hard errors via Django form validation; no warning/notification tier
FE-22 | Field, field-group, and form-level validation | ⚠️ | — | Field-level and form-level exist; no explicit field-group validation
FE-23 | Automated validation during form completion | 🐛 | bd-114, bd-458 | Validation logic exists but commented out in form_finalize.py:48 — forms submit even if invalid
FE-24 | Automated comparison to integration data (SAM.gov) | ❌ | — | No SAM.gov API, UEI field, or external data validation
FE-25 | Validation timing (during entry vs. review page) | ⚠️ | bd-114, bd-240 | Validates per-page on POST; review page shows errors via session flag; not inline during typing
Version Control Data Integrity
ID | Requirement | Status | Jira | Evidence
FE-30 | Multiple simultaneous form versions | ✅ | bd-222 | SemVerField on FormDefinition, version_number on FormEntry + unique_together constraints + is_active flag
FE-31 | Robust version history for federal staff | ✅ | — | Two-tier audit: FormAuditTrail + FormAuditDetail; FormSnapshotView reconstructs state
FE-32 | Historical comparison for recipients | ⚠️ | — | FormSnapshotView shows past state; no side-by-side diff view
Form Builder
ID | Requirement | Status | Jira | Evidence
FE-40 | Low-code/no-code form builder | 🔮 | — | Post-year-1 per MATRIX
FE-41 | Sandbox/testing space for form builder | 🔮 | — | Post-year-1
FE-42 | Faster form design iteration | ⚠️ | — | load_initial_forms + dump_schema commands; still requires developer involvement
Implementation Decisions
ID | Decision | Status | Jira | Evidence
FE-08 | Interview-style page-by-page POST flow | ✅ | bd-54, bd-85 | form_edit.py step/page navigation with ?step=N&page=N query params
FE-09 | JSON field storage for form data | ✅ | bd-427 (epic) | FormEntry.data = JSONField()
FE-10 | Pydantic schemas as single source of truth | ✅ | bd-427 (epic) | form_manager/schema/ defines UI structure, Django form classes, and validation
FE-11 | FormDefinition links to Python schema class | ✅ | bd-427 (epic) | schema_class string field dynamically imported
FE-33 | Status lifecycle: draft → submitted → amended → archived | ⚠️ | — | Model statuses exist; no view transitions to "amended"
FE-34 | Audit trail for all form actions | ✅ | — | FormAuditTrail + FormAuditDetail with field-level diffs and state reconstruction
FE-36 | Short form variant derived from long form | ✅ | bd-60 (epic) | TribalShortFormFields and TribalLongFormFields are separate schemas
FE-37 | Cross-form pre-population (Plan ← AR) | ❌ | — | No implementation; see FE-03
FE-38 | Periodic auto-save every 30-60s | ❌ | bd-37, bd-54, bd-235 | Save only on explicit form POST; no JS timers or debounce
FE-43 | Screener flow / form routing after login | ❌ | bd-332 (epic) | form_list shows all definitions as flat cards; no eligibility routing
FE-44 | Client-side caching (IndexedDB/localStorage) | ❌ | bd-459 | No browser storage APIs, no service worker
FE-45 | Connection state indicators | ❌ | bd-459 | No "Saved"/"Connection lost"/"Reconnected" UI
FE-46 | UEI as cross-form pre-population key | ❌ | — | No UEI field on OrganizationProfile
FE-47 | Concurrent edit conflict handling | ❌ | — | Boolean is_locked only; no optimistic locking
2 Form Submission Workflow Wf
ID | Requirement | Status | Jira | Evidence
WF-01 | Auto-create forms with pre-populated data | ❌ | — | form_start creates blank entries on user click; no schedule-driven creation
WF-02 | Show trends over time using previous year data | ❌ | — | No year-over-year comparison
WF-04 | Recipients can unsubmit forms | ❌ | bd-10 (epic) | "amended" status exists but no view transitions from submitted back to draft
WF-05 | Recipients can submit revisions | ❌ | — | No amend/revise view
WF-06 | Submit a form (distinct action) | 🐛 | — | form_finalize exists but validation commented out — always succeeds
WF-09 | Multi-step federal review and approval | 🔮 | — | Out of MVP scope
WF-11 | Save progress and return later | ✅ | bd-37, bd-54 | Forms save on page navigation POST; draft status preserved
WF-12 | Previously submitted data available | ⚠️ | — | Own entry loads on return; no cross-submission pre-population
WF-13 | Real-time alerts and notifications | 🔮 | — | Out of MVP scope
WF-14 | Deadline-aware notifications | 🔮 | — | No notification infrastructure
WF-15 | Multi-user form collaboration and routing | 🔮 | — | Out of MVP scope
WF-17 | Tracking and collaboration visibility | ❌ | — | No cross-role visibility
WF-18 | March 31 statutory submission deadline | ❌ | — | No deadline enforcement in application
3 Authentication Security As
ID | Requirement | Status | Jira | Evidence
AS-01 | Authentication with Login.gov | ❌ | bd-111 (epic), bd-13, bd-24, bd-35 | OIDC configured for Keycloak only; Login.gov deferred per AS-18
AS-03 | Gov users via login.acf.gov (Okta) | ❌ | bd-111 (epic), bd-474, bd-476 | No Okta configuration; Keycloak dev mock only
AS-05 | Auth Code Flow with PKCE + client secret | ✅ | bd-35, bd-46, bd-56 | django-oauth2-authcodeflow handles PKCE; server-side tokens
AS-06 | Keycloak for local dev | ✅ | bd-473 | Docker Compose with realm csfeer, CSV user seeding
AS-07 | Role-to-group mapping from JWT claims | ✅ | bd-477 | extend_user_with_roles maps realm_access.roles to Django groups
AS-08 | Role mappings (admin/staff/superuser) | ✅ | bd-477 | csfeer_admin → staff+superuser; wildcard creates groups
AS-10 | Auto-provision user + org on first login | ✅ | bd-476 | EmailOIDCAuthenticationBackend creates user, profile, org, membership
AS-11 | Group memberships re-synced every login | ✅ | bd-477 | user.groups.clear() runs every login; groups rebuilt from token
AS-14 | ATO within 18 months | ⚠️ | bd-438 (epic), bd-188, bd-469, bd-472 | Security patterns in code; ATO docs in progress
AS-18 | MVP basic sessions (Login.gov deferred) | ✅ | bd-473 | Current state: Django sessions via Keycloak OIDC
4 Integration Data Da
ID | Requirement | Status | Jira | Evidence
DA-01 | Read API for forms/submissions/bulk data | ⚠️ | bd-31 | 7 read-only GET endpoints via Django Ninja; no pagination, no rate limiting
DA-02 | Write API for pre-populated data import | ❌ | — | API is read-only; no POST/PUT/PATCH
DA-03 | Data exports via API, CSV, and human-readable | ⚠️ | — | API returns JSON; PDF exists; no CSV export
DA-04 | Export individual submissions as PDFs | 🐛 | bd-36, bd-49 | WeasyPrint works; synchronous in request cycle — blocking/DOS risk
DA-05 | Public-access links to submission portions | ❌ | — | No public/shareable link mechanism
DA-06 | Comprehensive API documentation | ✅ | bd-31 | Django Ninja auto-generates OpenAPI at /api/v1/docs
DA-07 | Real-time data access without perf degradation | ❌ | — | No read replica, caching, or query optimization
DA-14 | Staff export, review, and correct data errors | ❌ | — | Django admin only
DA-15 | Conditional-logic-aware PDF export | ❌ | — | PDF renders all sections regardless of conditional logic
5 Accessibility Design Ad
ID | Requirement | Status | Jira | Evidence
AD-01 | Section 508 WCAG AA compliance | ⚠️ | bd-471 (epic), bd-103, bd-461 | USWDS components accessible; no automated a11y testing
AD-02 | USWDS as design system | ✅ | bd-1 (epic) | django-cotton-uswds with 93 components; USWDS 3.13+
AD-05 | Clear progress in multi-step process | ✅ | bd-85, bd-450 | USWDS step indicator shows complete/current/incomplete
AD-06 | Plain, familiar language | ⚠️ | — | Present in templates; no systematic enforcement
AD-09 | Low-bandwidth/rural support | ❌ | bd-459 | No offline capability, no auto-save, no client caching
AD-13 | In-context field guidance | ⚠️ | — | ACFFieldMixin adds description; no companion doc integration
6 Permissions User Management Pm
ID | Requirement | Status | Jira | Evidence
PM-01 | Flexible permissions: read, write, export | ✅ | bd-6, bd-477 | Org-level admin/editor/viewer with permission checks
PM-02 | Self-service user management | ❌ | bd-108, bd-475 | users/views.py is empty; Django admin only
PM-03 | Hierarchical administration (sub/state/fed) | ❌ | — | Single flat OrganizationProfile; no hierarchy
PM-04 | Minimum permission levels per tier | ⚠️ | — | Org-level exists; no federal-tier or cross-org permissions
PM-05 | Varying permission levels | ⚠️ | — | View/edit/submit mapped to viewer/editor/admin; no export-specific perms
PM-08 | Authorization and access control | ⚠️ | bd-6 | Org-scoped authz works; out of MVP scope per MATRIX but partially done
7 Performance Reliability Pr
ID | Requirement | Status | Jira | Evidence
PR-02 | Scalable to 1,100 recipients + 75 staff | ❌ | — | No load testing, no pagination, sync PDF blocks workers
PR-04 | Real-time resource utilization monitoring | ❌ | bd-2 (epic), bd-102, bd-122 | No APM or metrics collection
PR-05 | Performance monitoring (response time, latency) | ❌ | bd-2 (epic) | File-based Django logging only
PR-10 | 24/7 operational availability | ⚠️ | — | HPA configured (min 2 / max 10) but miswired; no health check endpoint
PR-11 | ≥200 concurrent users | ❌ | — | No load testing; default gunicorn config
PR-13 | Modern browser support | ✅ | — | Standard Django + Alpine.js + USWDS
PR-14 | Reliable despite poor connectivity | ❌ | bd-459 | No auto-save, no client caching, no offline resilience
PR-15 | Test coverage >80% | ❌ | bd-481, bd-9, bd-33, bd-38, bd-0fea | ~51 unit + ~21 E2E tests; no coverage reporting; zero API tests
8 User Personas Roles Up
ID | Requirement | Status | Jira | Evidence
UP-01 | Three grantee role tiers (Approver/Contributor/Viewer) | ⚠️ | bd-15, bd-21, bd-108 | Admin/editor/viewer exist; naming differs from persona spec
UP-02 | SF-424M cross-referencing guidance | ❌ | — | No SF-424M references in schemas
UP-03 | Transmittal letter/attestation artifact | ❌ | — | No attestation model or signature capture
UP-04 | Portfolio dashboard for OCS staff | ❌ | bd-72, bd-221 (epic) | No cross-org view; staff see same interface as grantees
UP-05 | Batch review & structured export | ❌ | — | No bulk operations or cross-grantee comparison
UP-06 | Visual diff ("what changed from last year") | ❌ | — | Audit captures within-submission changes; no year-over-year
UP-07 | Simplified summary view for leadership | ❌ | — | No summary/dashboard view
UP-08 | Unified admin console | ❌ | — | Django admin only
9 Mvp Acceptance Criteria Ac
ID | Criterion | Status | Jira | Evidence
AC-01 | All three tribal forms with validation + save/submit | ⚠️ | bd-59 (epic), bd-60 (epic), bd-61 (epic) | Long + Short Form built; Tribal Plan not yet; validation commented out
AC-02 | Login.gov working for all pilot users | ❌ | bd-111 (epic) | Keycloak only; Login.gov deferred (contradicts this criterion)
AC-03 | CSV + PDF export functional | ⚠️ | bd-36, bd-49 | PDF works (synchronous); no CSV export
AC-04 | At least 10 tribal orgs submit during pilot | ❌ | — | Pre-pilot; no production deployment
10 Infrastructure Technology It
ID | Decision | Status | Jira | Evidence
IT-01 | Python 3.12, Django 6.0+ | ✅ | bd-460 (epic) | uv.lock resolves Django 6.0; Python 3.12 target
IT-02 | PostgreSQL (Aurora RDS) | ✅ | — | Terraform defines Aurora PostgreSQL 16.6 with IAM auth
IT-03 | AWS ECS (not Kubernetes) | ✅ | — | Superseded — moved to EKS/Kubernetes. Helm charts, ArgoCD, EKS Terraform all present
IT-04 | Alpine.js 3.15+ | ✅ | — | Alpine.js + mask plugin in webpack bundle
IT-05 | USWDS 3.13+ | ✅ | bd-1 (epic) | django-cotton-uswds with 93 components
IT-06 | Django Ninja for REST APIs | ✅ | bd-31 | 7 endpoints at /api/v1/
IT-07 | WeasyPrint for PDF generation | ✅ | bd-36, bd-49 | Synchronous in FormDownloadPDFView
IT-08 | Django Cotton for template components | ✅ | bd-57 | django_cotton_uswds app with pattern library
IT-09 | Keycloak for local dev auth | ✅ | bd-473 | Docker Compose with realm csfeer, CSV user seeding
11 Form Inventory Fi
ID | Form Name | Status | Jira | Notes
FI-01 | CSBG Tribal Plan and Application | ❌ | bd-61 (epic), bd-65, bd-66, bd-68, bd-69, bd-70, bd-230 | Design done; schema not yet built. Target Mar 31.
FI-02 | CSBG Tribal Annual Report (Long Form) | ✅ | bd-59 (epic), bd-16, bd-39, bd-47, bd-63, bd-104 | Schema exists and functional
FI-03 | CSBG Tribal Annual Report [Short Form] | ✅ | bd-60 (epic) | Schema exists and functional
12 Success Criteria Sc
ID | Criterion | Status | Jira | Evidence
SC-01 | 20+ tribal orgs submit via CORE | ❌ | — | Pre-pilot
SC-02 | ≥80% report easier than PDFs | ❌ | bd-48, bd-92, bd-104, bd-105 | Usability research planned; no survey mechanism built
SC-03 | 100% Section 508 compliance | ⚠️ | bd-471 (epic) | USWDS accessible; no automated verification
SC-04 | Zero OCIO security findings | ⚠️ | bd-438 (epic), bd-ha7h, bd-hze3, bd-octr | Security scans run; ATO in progress
SC-05 | Architecture docs complete for Phase II | ❌ | — | Not started
SC-06 | Platform supports simple and complex forms | ⚠️ | bd-59 (epic), bd-60 (epic) | Two tribal forms demonstrate spectrum
SC-07 | First measurable baseline for Tribal reporting | ❌ | — | Requires day-one telemetry (DL-15)
Coverage Summary
Category | Total | ✅ | ⚠️ | 🐛 | ❌ | 🔮 | Has Jira | No Jira
Form Engine (FE) | 28 | 11 | 6 | 1 | 10 | 0 | 20 | 8
Workflow (WF) | 13 | 1 | 1 | 1 | 6 | 4 | 2 | 11
Auth & Security (AS) | 10 | 7 | 1 | 0 | 2 | 0 | 10 | 0
Integration & Data (DA) | 9 | 1 | 2 | 1 | 5 | 0 | 3 | 6
Accessibility (AD) | 6 | 2 | 3 | 0 | 1 | 0 | 4 | 2
Permissions (PM) | 6 | 1 | 3 | 0 | 2 | 0 | 4 | 2
Performance (PR) | 8 | 1 | 1 | 0 | 6 | 0 | 4 | 4
User Personas (UP) | 8 | 0 | 1 | 0 | 7 | 0 | 3 | 5
MVP Acceptance (AC) | 4 | 0 | 2 | 0 | 2 | 0 | 3 | 1
Infrastructure (IT) | 9 | 8 | 0 | 0 | 1 | 0 | 6 | 3
Form Inventory (FI) | 3 | 2 | 0 | 0 | 1 | 0 | 3 | 0
Success Criteria (SC) | 7 | 0 | 2 | 0 | 5 | 0 | 4 | 3
Totals | 111 | 34 | 22 | 3 | 48 | 4 | 66 | 45
Notable Gaps No Jira Coverage
ID | Requirement | Severity | Area
FE-21 | Warning-tier validation | Medium | Validation
FE-47 | Concurrent edit handling | Low | Form Engine
DA-03 | CSV export | Blocking | MVP Acceptance (AC-03)
WF-04 | Unsubmit capability | High | Workflow
WF-05 | Revision submission | High | Workflow
WF-06 | Submit action (validation broken) | Blocking | Workflow
PM-02 | Self-service user management | High | Permissions
PR-02 | Scalability / load testing | High | Performance
PR-11 | 200 concurrent users | High | Performance

## MVP Gap Analysis
Mvp Scope
Form | Users | Build Status
Tribal Annual Report (Long Form) — FI-02 | ~30 orgs (>$50k funding) | Schema exists
Tribal Annual Report [Short Form] — FI-03 | ~30 orgs (≤$50k funding) | Schema exists
Tribal Plan and Application — FI-01 | ~66 orgs | Not yet built
Done Criteria
ID | Criterion | Status | Gap
AC-01 | All three tribal forms with validation + save/submit | ⚠️ | Tribal Plan not built; validation commented out in form_finalize.py:48
AC-02 | Login.gov working for pilot users | ❌ | Deferred per AS-18; conflicts with this criterion (see C-13 in MATRIX)
AC-03 | CSV + PDF export functional | ⚠️ | PDF works (synchronous/blocking); no CSV export
AC-04 | ≥10 tribal orgs successfully submit during pilot | ❌ | Pre-pilot; no production deployment
SC-01 | 20+ tribal orgs submit via CORE without reverting to PDFs | ❌ | Conflicts with AC-04 (10) and DL-11 (10-12) on pilot size
SC-02 | ≥80% of users report easier than PDFs | ❌ | No survey mechanism
SC-03 | 100% Section 508 compliance | ⚠️ | USWDS components accessible; no automated a11y testing
SC-04 | Zero OCIO security findings | ⚠️ | Strong security patterns; ATO docs in progress
SC-05 | Architecture docs complete for Phase II | ❌ | Not started
SC-06 | Platform supports both simple and complex forms | ⚠️ | Two tribal forms demonstrate complexity spectrum
SC-07 | First measurable baseline for Tribal reporting | ❌ | Requires day-one telemetry (DL-15)
1 Form Engine Core
Gap | Requirements | Severity | Jira | Notes
Tribal Plan form not built | FI-01 | Blocking | bd-61 (epic), bd-65, bd-70 | Third of three MVP forms; target Mar 31
Validation commented out in finalize | FE-23, WF-06 | Blocking | — | form_finalize.py:48 — forms submit even when invalid; no ticket
No warning-tier validation | FE-21 | Medium | — | All validation is blocking or nothing; PWS requires advisory warnings
No field-group validation | FE-22 | Low | — | Field-level and form-level exist; group-level gap
No auto-save | FE-38 | High | bd-235 | ⚠️ bd-37, bd-54 closed but only covered save-on-navigate, not periodic auto-save
No connection resilience | FE-44, FE-45 | High | bd-459 | No IndexedDB/localStorage, no connection state indicators; tribal users in rural/low-bandwidth areas
No screener/routing flow | FE-43 | Medium | bd-332 (epic) | Users see flat list of forms; no eligibility-based routing
No concurrent edit handling | FE-47 | Low | — | Boolean lock only; no optimistic locking; no ticket
2 Submission Workflow
Gap | Requirements | Severity | Jira | Notes
No unsubmit capability | WF-04 | High | bd-10 (epic) | "amended" status exists in model but no view transitions back to draft
No revision submission | WF-05 | High | — | No amend/revise workflow; no ticket
No auto-creation from schedules | WF-01 | Medium | — | Users manually start forms; no reporting-schedule-driven creation
No year-over-year trends | WF-02 | Medium | — | No previous-year data comparison
No cross-submission pre-population | WF-12 | Medium | — | Own entry loads; no prior submission data
No deadline awareness | WF-18 | Low | — | March 31 statutory deadline not enforced
No tracking visibility | WF-17 | Low | — | No cross-role status visibility
3 Authentication
Gap | Requirements | Severity | Jira | Notes
Okta/Login.gov not yet wired | AS-01, AS-03 | Blocked on ACF environment access | bd-111 (epic), bd-13, bd-24 | NGSC transition in progress; Okta/Login.gov integration follows environment access
ATO documentation incomplete | AS-14, AS-15 | Blocking (for pilot) | bd-438 (epic), bd-188, bd-469, bd-472 | Target May 29, 2026; multiple artifacts in progress
Claim structure uncertainty | AS-07 | Medium | bd-477 | Will Okta tokens emit roles in realm_access.roles (Keycloak convention) or a different claim path? Backend may need updating once Okta token structure is known
4 Data Integration
Gap | Requirements | Severity | Jira | Notes
No CSV export | DA-03, AC-03 | Blocking | — | Explicitly in MVP acceptance criteria; no ticket
Synchronous PDF generation | DA-04 | High | bd-49 | bd-36 closed (POC); bd-49 in_progress
No conditional-logic-aware PDF | DA-15 | Medium | — | Prints everything including non-applicable sections
API has no pagination | DA-01 | Medium | — | ⚠️ bd-31 closed but only covered scaffolding; pagination/rate-limiting never built
PII exposure via API | DA-01 | High | — | Full form data JSON, audit old/new values, org contact details exposed; no ticket
PII logged at INFO level | — | Critical | — | form_manager/utils.py:193+ logs form data; no ticket
5 Accessibility
Gap | Requirements | Severity | Jira | Notes
No automated a11y testing | AD-01, SC-03 | High | bd-471 (epic), bd-103 | 100% 508 compliance is a success criterion; no axe-core or equivalent in CI
No low-bandwidth support | AD-09 | High | bd-459 | Full page POST on every navigation; no offline resilience
6 Permissions
Gap | Requirements | Severity | Jira | Notes
No self-service user management | PM-02 | High | bd-108, bd-475 | No user management UI; Django admin only
No organizational hierarchy | PM-03 | Medium | — | Flat org model; no sub-recipient/state/federal tiers
7 Performance Observability
Gap | Requirements | Severity | Jira | Notes
No telemetry/instrumentation | PR-04, PR-05, DL-15 | High | bd-2 (epic) | Day-one instrumentation required for 90-day baseline; nothing exists
No load testing | PR-02, PR-11 | High | — | No evidence system handles 200 concurrent users; no ticket
No test coverage reporting | PR-15 | Medium | bd-481, bd-9 | >80% target; tool installed but not configured
Gunicorn not tuned | PR-11 | Medium | — | Default worker config; no explicit worker/thread/timeout settings
Deployment Blockers
Issue | Severity | Jira
Prod Docker image likely missing app code — only copies ./csfeer, not core/, users/, form_manager/ | Critical | bd-460 (epic)
Helm values/schema mismatch — templates reference different paths than values define | Critical | bd-460 (epic)
Ingress health check hits / which redirects to OIDC login (not 200) | High | —
Logging writes to /app/logs/*.log but K8s root filesystem is read-only, no writable volume mounted | High | —
SECRET_KEY env var name mismatch between Helm and Pydantic settings | High | —
CI/CD triggers commented out — no automated quality gates on PRs | High | bd-460 (epic)
Timeline
Target | Milestone | Status
Mar 1, 2026 | Landing page deployed | DL-01
Mar 15, 2026 | Tribal Annual Report (long form) complete | DL-02
Mar 31, 2026 | Tribal Plan and Application complete | DL-03
Mar 31, 2026 | ATO documentation package submitted | DL-04
Month 9 | Soft launch to 10-12 tribal orgs | DL-11
May 29, 2026 | ATO authorization | AS-15
Month 12 | Full rollout of remaining orgs | DL-12
Jira Coverage Notes
# | Gap | Severity | Action Needed
4 | Validation commented out in finalize | Blocking | Needs ticket
5 | PII in INFO logs | Critical | Needs ticket
7 | CSV export | Blocking | Needs ticket — MVP acceptance criterion
16 | Load testing | High | Needs ticket
20 | Year-over-year comparison | Medium | Needs ticket (if MVP)
Jira Coverage Notes
Gap | Jira | Issue | Why gap persists
Auto-save (FE-38) | bd-37, bd-54 | Both closed | Covered save-on-navigate only; periodic 30-60s auto-save never built
API hardening (DA-01) | bd-31 | Closed | Covered initial scaffolding; pagination, rate limiting, PII scoping not addressed
File attachments (FE-06) | bd-399 | Closed | USWDS component built; no storage backend wired

## Open Items
Conflicts C 1 Through C 13
# | Topic | Source A | Source B | Question | MVP-blocking? | Resolution Status
C-1 | Validation timing | [S29]: "while a grant-recipient fills out a form" (during-entry implied) | [S21]: review page validation; partial saves with invalid data allowed | When does validation fire? Determines form UX architecture. | Yes | Open — listed as open decision in gap analysis
C-2 | MVP pilot size | [S24]: 20+ tribal recipients | Other refs: 10–12 pilot cohort | Is 20+ the target or aspirational? Sets support staffing. | No | Open — listed as open decision in gap analysis
C-3 | FISMA classification | [S24] NFR4: FISMA Moderate ([S29] does NOT specify a level) | [S12]: Rev5-Low controls | Low or Moderate baseline? Determines entire security posture. | Yes | Open — listed as open decision in gap analysis
C-4 | MVP scope — APIs | [S29]: Must priority | [S21]: Out of scope; [S31]: stretch goal; [S39]: read-only only | Are APIs in MVP? If so, read-only per [S35]/[S39]. | No | Effectively resolved — read-only API exists (DA-01 ⚠️); 7 GET endpoints via Django Ninja
C-5 | MVP scope — Authorization | [S29]: Must priority (PM-01–PM-05) | [S21]: Out of scope | Is authz in MVP? Without it, how distinguish who can submit vs view? | Yes | Effectively resolved by implementation — org-level admin/editor/viewer roles implemented (PM-01 ✅, PM-08 ⚠️); MATRIX.md still marks PM-08 as conflict
C-6 | MVP scope — Notifications | [S29]: Must priority | [S21]: Out of scope | Are notifications in MVP? No deadline alerts otherwise. | No | Open — no notification infrastructure exists; WF-13/WF-14 are 🔮 deferred
C-7 | MVP scope — Approval workflows | [S29]: Must priority | [S21]: Out of scope | Are federal approval workflows in MVP? No approve/revise pipeline otherwise. | Yes | Effectively resolved by deferral — WF-09 marked 🔮 in MATRIX.md; review workflow questions remain open for Phase II (see D-07 below)
C-8 | Contract duration | [S29]: 12+12 = 24 months | [S02]: "1 year + 9 month option" = 21 months | Which is correct? Affects planning horizon. | No | Open
C-9 | User satisfaction metric | [S24]: ≥80% easier than PDFs | Other refs: ≥4/5 satisfaction score | Different measurement frameworks. | No | Open
C-10 | PDF generation tech | [S18]: WeasyPrint | Other refs: headless Chrome | Which approach? Determines deployment constraint. | No | Effectively resolved — WeasyPrint in production (IT-07 ✅); synchronous, needs async wrapper
C-11 | Competing platform | CSFEER (this project) | [S13]: $1.2M GrantSolutions dev | What happened to the OLDC effort? Competitive, fallback, or abandoned? | No | Open
C-12 | Transition plan duration | [S33]: 4 weeks (2 sprint cycles) | [S35]: 90-day plan (doc audit → training → parallel ops) | 4 weeks vs 90 days — order-of-magnitude difference. | No | Open
C-13 | Login.gov in MVP? | [S39] AC-02: Login.gov working for all pilot users | [S31] AS-18: MVP uses basic sessions; Login.gov deferred | Acceptance criterion contradicts Q1 plan. | Yes | Open — auth blocked on ACF NGSC environment access; not a code problem (see D-04)
Risks R 01 Through R 14
ID | Risk | Prob | Impact | Mitigation | Source
R-01 | Government shutdown | Med | Med | Delivery plan for shutdown scenarios; non-blocking work sequenced first; ATO prep runs in parallel | [S16]
R-02 | Tribal consultation | Low | High | Ongoing consultation, opt-in approach, transparent communication, respect for sovereignty | [S16]
R-03 | Login.gov complexity | Low | Med | Early technical spikes; close coordination with ACF; staged integration and testing | [S16]
R-04 | Data migration challenges | Med | Med | Limit MVP pre-population to high-confidence data only; document expansion path for Phase II | [S16]
R-05 | User adoption | Med | High | Tribal-informed design, usability testing, training, phased onboarding, help desk support | [S16]
R-06 | ATO/Security reviews | Low | High | Parallel ATO workstream; weekly syncs; early control implementation; #1 risk per [S35] (p×i = 0.45) | [S17]; [S35]
R-07 | Dependency on external reviews | Med | Med | Questions staged early; assumptions documented; flexible sequencing | [S17]
R-08 | Non-gov user auth path uncertainty | ? | ? | TBD — could delay development or require rework. Relates to C-13 and D-04. | [S10]
R-09 | PIA classification guidance delay | ? | ? | Could block system deployment and ATO approval. See Q-08. | [S10]
R-10 | Competing GrantSolutions implementation ($1.2M–$1.71M) | ? | ? | Relationship to CSFEER unclear — competitive? fallback? abandoned? See C-11. | [S13]
R-11 | State resistance to platform adoption (e.g., NJ "empower") | ? | ? | OCS can issue DCLs (Dear Colleague Letters) | [S02]
R-12 | Attestation/signature workflow unclear | ? | ? | How does tribal council sign-off work digitally? See Q-12 (new). | [S36]
R-13 | Policy interpretations may alter form logic mid-development | ? | Med | OMB form definitions and OCS validation rules are dependencies | [S36]
R-14 | OLDC user data isolation | Med | Med | CSFEER creating users independently from OLDC; requires API integration to import existing users; Thomas Oldfield (ACF Tech) is data liaison | [S38]
R-15 | Deployment artifacts broken | High | High | Prod Docker image likely missing app code; Helm chart mismatches; health check fails. New — from architectural review. | Arch review
R-16 | PII exposure (API + logs) | High | High | API returns full form data JSON with PII; INFO-level logging dumps form data. New — from architectural review. | Arch review
Open Decisions D 01 Through D 08
ID | Decision | Context | Traces to | Owner
D-01 | Validation timing | Inline during entry vs. review-page-only? PWS says "during entry"; tech spec says review-page. Determines entire form UX. | C-1, FE-25 | Product
D-02 | Pilot size | 10 (AC-04) vs. 10-12 (DL-11) vs. 20+ (SC-01)? Affects support staffing and success criteria. | C-2 | Product
D-03 | FISMA baseline | Low (AS-A10/S12) vs. Moderate (S24/PR-12)? Affects ATO scope, control implementation, and timeline. | C-3 | Security/Product
D-04 | Okta token claim mapping | Will Okta emit roles in realm_access.roles (Keycloak convention) or different claim path? Backend role sync depends on this. Testable once NGSC access granted. | C-13, AS-07 | Tech
D-05 | Async infrastructure | Celery+Redis? Django-Q? Task queue choice affects PDF generation, email, notifications. No async capability exists today. | Arch review | Tech
D-06 | Multi-tenancy isolation model | Tenant, permission, data partitioning, or hybrid? Constrains all foundation-layer deliverables. Not yet designed. | VALUE_STREAM_ANALYSIS.md | Tech/Arch
D-07 | Federal review workflow design | Six sub-questions (all post-MVP but design affects data model now): Sequential vs. parallel steps? Conditional routing? Unanimous vs. any-one-approves? Who configures? Delegation rules? Reviewer permission tiers? | C-7, WF-09, MATRIX.md [WS-07/08/09] | Product
D-08 | Login.gov in MVP? | AC-02 says yes; AS-18 says deferred. Blocked on ACF NGSC environment access. Not a code problem — OIDC plumbing is built. | C-13, R-08 | Product/ACF
Open Questions Q 01 Through Q 12
ID | Question | Context | Traces to
Q-01 | What are the specific validation rules for each of the 3 Tribal forms? | Rules live in the forms themselves / SmartForms XSD, not in Confluence docs | FE-20
Q-02 | How do Tribal recipients currently collaborate on form preparation? | Affects multi-user workflow design | WF-15
Q-03 | What analytics/reporting format does Congress require? | Melanie Durley is SME; requirements undocumented | DA-03
Q-04 | How should biannual vs annual Plan Application submissions be handled? | Affects form scheduling logic | WF-01
Q-05 | What are the specific UEI/SAM.gov integration points for automated mismatch detection? |  | FE-24
Q-06 | Field-level mapping between OLDC columns and CSFEER schema fields | FY24 export conventions documented; field-level mapping unknown | R-04, R-14
Q-07 | Form definition versioning vs submission snapshot history — what exactly is required? |  | FE-30, FE-31
Q-08 | PIA classification: "electronic information collection" vs "application"? | Rubric needed from privacy team (Tobi/Oyindasola) | R-09
Q-09 | SORN timeline and scope | Confirmed required but no timeline documented; full PII inventory needed beyond email | R-09
Q-10 | Notification SLA/deadline enforcement and escalation rules — what are the business rules? |  | C-6, WF-14, WF-18
Q-11 | CSV export format and scope — what columns, what granularity, who consumes it? | MVP acceptance criterion (AC-03) with no specification | DA-03
Q-12 | How does tribal council sign-off/attestation work digitally? | No attestation model, signature capture, or transmittal letter workflow | R-12, UP-03
Summary
Category | Total | Open | Resolved/Deferred
Conflicts (C-xx) | 13 | 6 blocking + 3 non-blocking | 4 effectively resolved
Risks (R-xx) | 16 | 16 (7 unscored) | 0
Decisions (D-xx) | 8 | 8 | 0
Questions (Q-xx) | 12 | 12 | 0
Total | 49 | 45 | 4